Meeting Report & Summary

Key Discussion Points, Outcomes & Action Items

📝 Complete within 24 hours of the meeting. Share with client and internal team for alignment.

1. Meeting Overview

| Date | 15 March 2025 |
| --- | --- |
| Location | Davis & Shirtliff HQ, Nairobi |
| Duration | 95 minutes (ran 5 min over) |
| Attendees — Partner | James Kariuki (Dir.), Mary Wanjiku (Procurement), Tom Odhiambo (Technical) |
| Attendees — SCA | Jean-Pierre Nkurunziza (Lead), via video: Dr. Stefan Mueller (Client) |

2. Key Discussion Points

Product Fit

Davis & Shirtliff expressed strong interest in the X200 and X400 models. Their technical team confirmed compatibility with existing industrial installations. Key concern: spare parts availability and local repair capability.

Market Opportunity

D&S sees immediate demand from 15–20 manufacturing clients currently using manual monitoring. Food processing sector identified as highest-priority vertical.

Commercial Terms

D&S requested 40% margin (vs. offered 35%). Open to Kenya-only exclusivity for Year 1, with East Africa review after targets met. MOQ discussion: 20 units initial order acceptable.

3. Outcomes & Decisions

- Both parties agree to proceed with a 3-month pilot program

- Pilot scope: 10 X200 units placed with 3 D&S clients (food processing)

- D&S to provide technical staff for SCA-led training (2-day program)

- Margin agreed at 37% — split the difference

- Payment terms: 60 days net, LC for first order

4. Action Items

| Action Item | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Send revised pricing proposal with 37% margin | SCA / Jean-Pierre | 18 Mar | Pending |
| Share pilot agreement draft | SCA Legal | 20 Mar | Pending |
| Identify 3 pilot clients and confirm sites | D&S / James | 25 Mar | Pending |
| Arrange product shipment (10x X200) | TechFlow / Stefan | 1 Apr | Pending |
| Schedule 2-day technical training | SCA / Jean-Pierre | 10 Apr | Pending |

5. Next Steps

- SCA to circulate this report to all parties by 16 March

- Follow-up call scheduled for 25 March to confirm pilot logistics

- Formal pilot agreement to be signed by 1 April 2025

6. Overall Assessment

Meeting was highly productive. Davis & Shirtliff has strong infrastructure, motivated team, and clear market access. Recommended to proceed with pilot. Probability of long-term partnership: HIGH (85%).