Contract Negotiation Support

Key Terms, Tracker & Risk Flags

📝 Use this template to track all negotiation points. Update after each negotiation session.

1. Negotiation Overview

| Parties | TechFlow Solutions GmbH ↔ Davis & Shirtliff Ltd |
| --- | --- |
| Agreement Type | Exclusive Distribution Agreement |
| Territory | Kenya |
| Term | 2 years, renewable |
| Negotiation Start | 20 March 2025 |
| Target Close | 15 April 2025 |
| SCA Lead | Jean-Pierre Nkurunziza |

2. Key Terms Tracker

| Term | Client Position | Partner Position | Status | Resolution |
| --- | --- | --- | --- | --- |
| Margin | 35% | 40% | Open | Proposed 37% |
| Exclusivity | Kenya only | East Africa | Open | Kenya Y1, review Y2 |
| MOQ | 20 units/quarter | 50 units/quarter | Agreed | 30 units/quarter |
| Payment Terms | 30 days | 90 days | Agreed | 60 days net |
| Marketing Fund | €3K/year | €10K/year | Open | €5K co-funded |
| Training | Online only | On-site 2x/year | Agreed | 1 on-site + online |
| IP/Trademark | License only | Sub-license rights | Open | License, no sub |
| Termination | 30 days notice | 180 days notice | Open | 90 days proposed |

3. Risk Flags

- 🔴 HIGH: Exclusivity scope — East Africa request exceeds client mandate

- 🟡 MEDIUM: Margin gap — 2% difference impacts client profitability

- 🟡 MEDIUM: IP sub-licensing — potential brand control issues

- 🟢 LOW: Payment terms — resolved at 60 days

4. Concessions Log

| Client Concession 1 | Increased margin from 35% to 37% |
| --- | --- |
| Client Concession 2 | Agreed to €5K co-marketing fund (was €3K) |
| Partner Concession 1 | Reduced MOQ from 50 to 30 units/quarter |
| Partner Concession 2 | Accepted Kenya-only for Year 1 |

5. Next Negotiation Session

| Date | 28 March 2025 |
| --- | --- |
| Focus Items | Exclusivity expansion terms, termination clause |
| Preparation Required | Draft compromise language for territory review clause |