## Follow-Up Tracker
Follow-Up Coordination Tracker
Track all post-meeting follow-ups, responsibilities, and deal progress
# | Company | Action Item | Owner | Follow-Up Date | Deadline | Status | Priority | Stage | Notes
1 | Davis & Shirtliff | Send revised pricing (37% margin) | SCA / Jean-Pierre | 16-Mar-2025 | 18-Mar-2025 | Done | High | Negotiation | Sent via email, confirmed received
2 | Davis & Shirtliff | Share pilot agreement draft | SCA Legal | 18-Mar-2025 | 20-Mar-2025 | In Progress | High | Negotiation | Legal reviewing final draft
3 | Davis & Shirtliff | Identify 3 pilot client sites | D&S / James | 20-Mar-2025 | 25-Mar-2025 | Pending | High | Pilot Setup | Awaiting D&S confirmation
4 | Orion East Africa | Send exclusivity terms proposal | SCA / Jean-Pierre | 19-Mar-2025 | 22-Mar-2025 | Done | High | Negotiation | Sent, awaiting feedback
5 | Orion East Africa | Schedule follow-up call | SCA / Jean-Pierre | 25-Mar-2025 | 28-Mar-2025 | Pending | Medium | Follow-Up
6 | CFAO Group | Follow up with regional director | SCA / Jean-Pierre | 25-Mar-2025 | 1-Apr-2025 | Pending | Medium | Qualification | Need intro from Marie Koné
7 | Davis & Shirtliff | Arrange product shipment (10 units) | TechFlow / Stefan | 1-Apr-2025 | 15-Apr-2025 | Not Started | High | Pilot Setup | Pending agreement signature
8 | Davis & Shirtliff | Schedule technical training | SCA / Jean-Pierre | 5-Apr-2025 | 10-Apr-2025 | Not Started | Medium | Onboarding | 2-day program, Nairobi
PIPELINE SUMMARY
Total Actions | 8
Done | 2
In Progress | 1
Pending | 3
Not Started | 2
Completion Rate | 25%